## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Setup & Environment Configuration | MUST HAVE | No Dependency | Vamsi | 3- Completed
S1 | S1 | US-002 | Install Nmap + Python dependencies (Cell 1) | MUST HAVE | Nmap Binary | Vamsi | 3- Completed
S2 | S2 | US-003 | Implement scanner.py — Nmap XML parser | MUST HAVE | python-nmap | Vamsi | 3- Completed
S2 | S2 | US-004 | Integrate VirusTotal API (check_virustotal) | MUST HAVE | VT API Key | Vamsi | 3- Completed
S3 | S3 | US-005 | Build analyser.py — 3D Risk Scoring Engine | MUST HAVE | scanner.py | Vamsi | 3- Completed
S3 | S3 | US-006 | Implement severity classification logic | MUST HAVE | analyser.py | Vamsi | 3- Completed
S4 | S4 | US-007 | Build database.py — SQLite scan history | MUST HAVE | SQLite3 | Vamsi | 3- Completed
S4 | S4 | US-008 | Build emailer.py — HTML email + PDF report | MUST HAVE | fpdf2, smtplib | Vamsi | 3- Completed
S5 | S5 | US-009 | Build Streamlit dashboard — Home page | MUST HAVE | Streamlit | Vamsi | 3- Completed
S5 | S5 | US-010 | Build Overview page (charts & gauges) | SHOULD HAVE | Plotly | Vamsi | 3- Completed
S6 | S6 | US-011 | Build Analysis page (scatter, heatmap, VT) | SHOULD HAVE | Plotly | Vamsi | 3- Completed
S6 | S6 | US-012 | Build History page — SQLite trend charts | SHOULD HAVE | database.py | Vamsi | 3- Completed
S7 | S7 | US-013 | Build FastAPI REST service (api.py) | SHOULD HAVE | FastAPI, Slowapi | Vamsi | 3- Completed
S7 | S7 | US-014 | Build Export page (PDF + CSV download) | SHOULD HAVE | fpdf2 | Vamsi | 3- Completed
S8 | S8 | US-015 | Build Email Alert page with validation | COULD HAVE | emailer.py | Vamsi | 3- Completed
S8 | S8 | US-016 | Testing, bug fixes & final documentation | MUST HAVE | All modules | Vamsi | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 88 | 37 | 35 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Project Setup & install all Python dependencies | 2025-01-06 | 2025-01-07 | Vamsi | Others | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Install & verify Nmap binary, test on scanme.nmap.org | 2025-01-08 | 2025-01-09 | Vamsi | Others | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 3 | Write scanner.py — run_nmap_scan + parse_nmap_xml | 2025-01-13 | 2025-01-15 | Vamsi | Coding | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 4 | Integrate VirusTotal API — check_virustotal + run_full_pipeline | 2025-01-16 | 2025-01-17 | Vamsi | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 5 | Build analyser.py — exposure, threat, context scoring | 2025-01-20 | 2025-01-22 | Vamsi | Coding | 3- Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 1900-01-05 | Severity classification + recommendations mapping | 2025-01-23 | 2025-01-24 | Vamsi | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 1900-01-06 | Build database.py — init_db, save_scan, load_history | 2025-01-27 | 2025-01-28 | Vamsi | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 1900-01-07 | Build emailer.py — PDF generation + MIME email with attachment | 2025-01-29 | 2025-01-31 | Vamsi | Coding | 3- Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 1900-01-08 | Build Streamlit home — scan trigger, posture banner, host table | 2025-02-03 | 2025-02-05 | Vamsi | Build | 3- Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 1900-01-09 | Build Overview page — bar, pie, radar, treemap, gauges | 2025-02-06 | 2025-02-07 | Vamsi | Build | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 1900-01-10 | Build Analysis page — scatter, heatmap, VT engine chart | 2025-02-10 | 2025-02-12 | Vamsi | Build | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 1900-01-11 | Build History page — trend charts + drill-down | 2025-02-13 | 2025-02-14 | Vamsi | Build | 3- Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 1900-01-12 | Build FastAPI api.py — endpoints + rate limiting | 2025-02-17 | 2025-02-19 | Vamsi | Build | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | 1900-01-13 | Build Export page — PDF + CSV download buttons | 2025-02-20 | 2025-02-21 | Vamsi | Build | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | 1900-01-14 | Build Email Alert page — validation + send button | 2025-02-24 | 2025-02-26 | Vamsi | Build | 2- In Progress | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | 1900-01-15 | Testing, debug MIME PDF bug, final cleanup | 2025-02-27 | 2025-02-28 | Vamsi | System Test | 2- In Progress | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Setting up virtual environment — package versions conflicting | Fixed by pinning versions in requirements and using Python 3.11
Sprint 1 | Day 2 | Nmap binary not found on Windows PATH | Added nmap to system PATH and verified with nmap --version
Sprint 2 | Day 4 | VirusTotal API returning 404 for private IPs | Added guard — skip VT lookup for RFC1918 addresses
Sprint 2 | Day 5 | Nmap scan timeout on -p- flag for slow networks | Added --min-rate 1000 flag to speed up scanning
Sprint 3 | Day 7 | Risk score always 0 — exposure_score function not applying correctly | Debugged apply() axis and fixed SERVICE_RISK dict lookup
Sprint 3 | Day 8 | Unicode characters in service names crashing fpdf2 | Added _safe_str() with ASCII encode/ignore fallback
Sprint 4 | Day 10 | SQLite path error on Windows — forward slash issue | Used os.path.normpath() to fix path separators
Sprint 4 | Day 11 | PDF not attaching to email — MIME structure wrong | Fixed by attaching HTML directly to MIMEMultipart('mixed') not nested alternative
Sprint 5 | Day 13 | Streamlit session_state df check raising ValueError for DataFrame | Fixed with 'is None' check instead of truthiness check
Sprint 5 | Day 14 | Plotly chart not rendering — xaxis range=[0,11] on date axis | Removed broken range from xaxis — only set yaxis range
Sprint 6 | Day 16 | History page showing empty charts even with data | Fixed sort_values('id') before plotting to ensure chronological order
Sprint 7 | Day 18 | FastAPI rate limiter crashing on startup | Fixed by correctly registering RateLimitExceeded handler on app
Sprint 8 | Day 20 | Email app password validation rejecting valid 19-char passwords | Fixed by stripping spaces before checking length — Google adds spaces in display

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-01-06 | 2025-01-09 | Vamsi | Write scanner.py tests before integrating VT | Skipping error handling in subprocess calls | Reviewing Nmap docs for new flags | Added try/except around subprocess.run and verified XML parsing
2 | Sprint 2 | 2025-01-13 | 2025-01-17 | Vamsi | Cache VT results to avoid duplicate API calls | Making VT calls for private/reserved IPs | Using pandas DataFrames for structured scan data | Added vt_cache dict so each unique IP is only queried once per scan
3 | Sprint 3 | 2025-01-20 | 2025-01-24 | Vamsi | Test risk scoring with edge cases (all Low, all Critical) | Hardcoding risk weights in multiple places | Keeping scoring logic modular and well-commented | Centralised weights as constants at top of analyser.py
4 | Sprint 4 | 2025-01-27 | 2025-01-31 | Vamsi | Verify PDF attachment on every run — not just after fix | Using nested MIMEMultipart alternative inside mixed | Saving scan results to SQLite for historical tracking | Fixed MIME structure — HTML now attached directly to mixed; PDF attaches correctly
5 | Sprint 5 | 2025-02-03 | 2025-02-07 | Vamsi | Add loading spinners for each scan phase | Using session_state truthiness check on DataFrames | Using progress bars to show scan stages to user | Replaced 'if df' with 'if df is None' to fix ValueError ambiguity
6 | Sprint 6 | 2025-02-10 | 2025-02-14 | Vamsi | Add filter by date range to history page | Using range=[0,11] on date-type x-axis in Plotly | Sorting history by scan id before plotting | Removed broken xaxis range — charts now render correctly
7 | Sprint 7 | 2025-02-17 | 2025-02-21 | Vamsi | Add /health endpoint and API key rotation support | Mixing route-level and app-level rate limit config | Using Pydantic models for strict API request validation | Correctly registered RateLimitExceeded handler — API now starts without errors